## Sprint Backlog
Sprint Back Log
Task ID | Task | Description | Story ID | Backlog ID | Sprint# | State | Estimate Time (Hours) | Assign to | Note
Login và Quản lý sinh viên cho cán bộ đào tạo
T01 | Thiết kế database |  | RQ01 | RL01 |  | New | 3 | Tuấn
T02 | Kết nối database vào chương trình |  |  |  |  | New | 5 | Tuấn
T03 | Tạo giao diện chương trình |  | RQ01 |  |  | New | 6 | Tri
T04 | Code chức năng đăng nhập |  | RQ01 |  |  | New | 8 | Triều
T05 | Code: Bắt lỗi |  |  |  |  | New | 10 | Tri
T07 | Tạo giao diện chương trình |  |  |  |  | New | 6 | Tri
T08 | Code: Thêm sinh viên có upload ảnh |  | RQ05 |  |  | New | 5 | Triều
T09 | Code: Update sinh viên |  | RQ05 |  |  | New | 8 | Tri
T10 | Code: Xóa sinh viên |  | RQ05 |  |  | New | 8 | Triều
T11 | Code: Lưu vào database |  |  |  |  | New | 8 | Tuấn
T12 | Kiểm thử |  |  |  |  | New | 13 | Dũng
Quản lý điểm cho giảng viên
T13 | Thiết kế database |  |  | RL02 |  | New | 3 | Tuấn
T14 | Kết nối database vào chương trình |  |  |  |  | New | 5 | Tuấn
T15 | Tạo giao diện chương trình |  |  |  |  | New | 6 | Tri
T16 | Code: Thêm điểm |  | RQ03 |  |  | New | 5 | Triều
T17 | Code: Update điểm |  | RQ04 |  |  | New | 5 | Tri
T18 | Code: Tính điểm trung bình khi cập nhật |  | RQ06 |  |  | New | 8 | Triều
T19 | Code: Bắt lỗi |  |  |  |  | New | 10 | Tri
T20 | Code: hiển thị thông tin từ table lên form |  |  |  |  | New | 3 | Tuấn
T21 | Code: Điều hướng |  |  |  |  | New | 4 | Trung
T22 | Code: Sửa điểm |  | RQ03 |  |  | New | 5 | Triều
T23 | Code: Xóa điểm |  | RQ03 |  |  | New | 5 | Tuấn
T24 | code: Tìm sinh viên theo mã |  | RQ06 |  |  | New | 8 | Tri
T25 | Kiểm thử |  |  |  |  | New | 13 | Triều

## Release Backlog
Backlog ID | Backlog | STORY / FEATURE / REQUEST |  |  | Story ID | Priority | Business Value | Sprint# | State | Note
|  | As a/an [User role] | I want to [Goal] | So that [reason]
RL01 | Login, Quản lý sinh viên | Cán bộ đào tạo | Tôi cần một username và password riêng cho cán bộ đào tạo | Để những người bên cán bộ đào tạo có thể đăng nhập vào phần mềm quản lý sinh viên. | RQ01 | 1 | Low | 1 | New
|  | Giảng viên | Tôi cần một username và password riêng cho giảng viên | Để những giảng viên có thể đăng nhập vào phần mềm quản lý điểm của sinh viên. | RQ05 | 1 | Low | 1 | New
|  | Cán bộ đào tạo | Tôi muốn có chức năng thêm sinh viên | Nhằm mục đích để thêm sinh viên. | RQ02 | 2 | Medium | 3 | New
|  | Cán bộ đào tạo | Tôi muốn có chức năng xóa sinh viên | Nhằm mục đích để xóa sinh viên. | RQ03 | 2 | Medium | 3 | New
|  | Cán bộ đào tạo | Tôi muốn có chức năng update sinh viên | Nhằm mục đích để update sinh viên. | RQ04 | 2 | Medium | 3 | New
RL02 | Quản lý điểm sinh viên | Giảng viên | Tôi muốn có chức năng thêm điểm | Nhằm mục đích để thêm điểm sinh viên. | RQ09 | 2 | Medium | 2 | New |  | rl1+rl3
|  | Giảng viên | Tôi muốn có chức năng sửa điểm | Nhằm mục đích để sửa sinh viên. | RQ11 | 2 | Medium | 2 | New
|  | Giảng viên | Tôi muốn có chức năng xóa điểm | Nhằm mục đích để xóa sinh viên. | RQ10 | 2 | Medium | 2 | New
|  | Giảng viên | Tôi muốn có chức năng update điểm | Nhằm mục đích update điểm cho sinh viên. | RQ12 | 2 | Medium | 2 | New
|  | Giảng viên | Tôi muốn có chức năng tính lại điểm trung bình | Nhằm mục đích để tính lại điểm trung bình dễ dàng, không bị sai sót | RQ07 | 3 | High | 2 | New
|  | Giảng viên | Tôi muốn có chức năng tìm sinh viên theo mã | Nhằm mục địch tìm sinh viên một cách dễ dàng | RQ06 | 2 | Medium | 2 | New
|  | Giảng viên | Tôi muốn có chức năng hiển thị 3 sinh viên có điểm cao nhất | Nhằm mục đích để trao thưởng cho 3 sinh viên suất xắc nhất | RQ08 | 3 | High | 2 | New

## Product Backlog
ID | STORY / FEATURE / REQUEST |  |  | Priority | Business Value | Acceptance Criteria | State | Note
| As a/an [User role] | I want to [Goal] | So that [reason]
RQ01 | Cán bộ đào tạo | Tôi muốn Username và Password riêng cho cán bộ đào tạo | Nhằm mục đích truy cập vào phần quản lý sinh viên riêng của cán bộ đào tạo, có độ bảo mật cao. | 1 | Low |  | New
RQ02 | Cán bộ đào tạo | Tôi muốn có chức năng Thêm sinh viên | Nhằm mục đích để thêm sinh viên. | 3 | Medium |  | New
RQ03 | Cán bộ đào tạo | Tôi muốn có chức năng Xóa sinh viên | Nhằm mục đích để xóa sinh viên. | 3 | Medium |  | New
RQ04 | Cán bộ đào tạo | Tôi muốn có chức năng Update sinh viên | Nhằm mục đích để update sinh viên. | 3 | Medium |  | New
RQ05 | Giảng viên | Tôi muốn có một Username và Password riêng cho giảng viên | Nhằm mục đích truy cập vào phần quản lý sinh viên riêng của giảng viên , có độ bảo mật cao. | 1 | Low |  | New
RQ06 | Giảng viên | Tôi muốn có thêm chức năng tìm theo mã | Nhằm mục địch tìm sinh viên một cách dễ dàng | 2 | Medium |  | New
RQ07 | Giảng viên | Tôi muốn có chức năng tính lại điểm trung bình | Nhằm mục đích để tính lại điểm trung bình dễ dàng, không bị sai sót | 3 | High |  | New
RQ08 | Giảng viên | Tôi muốn có chức năng hiển thị danh sách 3 sinh viên có điểm tổng kết cao nhất mỗi môn học. | Nhằm mục đích để trao thưởng cho 3 sinh viên suất xắc nhất | 3 | High |  | New
RQ09 | Giảng viên | Tôi muốn có chức năng Thêm điểm | Nhằm mục đích để thêm điểm sinh viên. | 2 | Medium |  | New
RQ10 | Giảng viên | Tôi muốn có chức năng Xóa điểm | Nhằm mục đích để xóa điểm sinh viên. | 2 | Medium |  | New
RQ11 | Giảng viên | Tôi muốn có chức năng Sửa điểm | Nhằm mục đích để sửa điểm sinh viên. | 2 | Medium |  | New
RQ12 | Giảng viên | Tôi muốn có thêm chức năng update điểm | Nhằm mục địch update điểm cho sinh viên. | 2 | Medium |  | New

## RULE
Title: Brief description of the PBI. The title of a PBI should represent the intent of the PBI.
Iteration: Indicate the sprint in which a PBI is implemented. When you first enter a PBI into TFS, iteration defaults to the current project, meaning that it's not yet scheduled for a sprint. During the sprint planning meeting, when the team commits to implementing a PBI, you set this field to the iteration representing the sprint.
Assigned To: Indicates the owner of a PBI. The product owner who's assigned to the PBI is responsible for answering questions and providing details about the PBI. This person is also responsible for verifying that the PBI meets acceptance criteria before the team finishes the sprint. When a PBI is first created, the Assigned To field defaults to the user entering the PBI, so it's best to set it to the product owner at that point.
State: Use the State field to track the current state of a PBI.
New: The PBI is entered into TFS. It may be just the initial text of a user story, or it may be fully defined with test cases and acceptance criteria.
Approved: The PBI has been approved by the product owner and is a candidate to be assigned to a sprint at the sprint planning meeting.
Committed: The PBI has been assigned to a sprint, and the team has committed to completing it.
Removed: The PBI is no longer needed. This is useful when you're pruning the backlog to remove duplicates, to consolidate similar PBIs, or to simply remove the PBIs that are such low priority that they will never be built.
Done: The PBI is complete, and the product owner has tested and verified it.
Reason: Reason is a read - only field that is predefined based on the state and transition of the PBI.
New
New Backlog Item : The PBI was just entered but not yet prioritized or estimated.
Reconsidering Backlog Item : The item had been removed but was reconsidered and is now back in the backlog.
Approved
Approved by the Product Owner : The PBI was approved by the product owner and is now ready to be included in a sprint.
Work Stopped : The PBI had been committed to a sprint, but the team decided to stop work on it and put it back in the backlog for future sprint.
Committed : Commitment Made by the Team : The team has committed to implement the PBI in a sprint.
Additional Work Found: The PBI was previously considered done, but more work was found, so it's back in the backlog.
Removed: The PBI was removed from the backlog.
Done: The work on the PBI is finished.
Backlog Priority: Used to determine the position of the PBI on the product backlog. New PBIs default to a backlog priority of 1,000. This field represents an item's location in the backlog, not its business value. It indicates when the PBI should be scheduled, relative to other items on the list.
Effort: Used to track the estimated effort required to implement a PBI, relative to other PBIs in the release. Relative is the operative word here, as the effort is not in terms of hours or days. Rather, it's a just a number used to compare the relative effort required for PBIs.
Business Value: Used to track the amount of business value delivered by a PBI. You should choose a number between 1 and 100 to represent the amount of business value that implementing the PBI will deliver to your customers. Higher numbers imply greater business value. A PBI with a low business value and a high effort estimate probably won't get scheduled into a sprint and will remain on the product backlog.
Description: Used to provide a detailed description of a PBI. This is where the product owner describes what the feature does and who needs it. If you're defining PBIs via user stories, then this is the written record of the feature.
Acceptance Criteria: Used to provide a bulleted list of criteria a PBI must meet before it will be accepted as done. The product owner defines the acceptance criteria either when initially creating the PBI or when the PBI is added to a sprint. It's critical to have sufficient information in this field for a PBI because these are the criteria against which the team will build the feature during the sprint.
Conclusion
In this article, we have seen that the product backlog is the list of requirements for the system. It is the central focus of a Scrum team, representing the features that the team will build into the product. The product owner defines and prioritizes the PBIs. Each PBI stores the details of one product feature. It describes its business benefit, test cases, and acceptance criteria.